## Cover
Hitachi Vantara Vietnam Co., Ltd.
PRODUCT BACKLOG AND RELEASE PLAN
|  | Reference: TL-AGL-002 |  | Revision: <>
PRODUCT BACKLOG AND RELEASE PLAN
FOR
Full-stack CoE Management System
DOCUMENT CHANGE LOG
Revision | Description | Author | Date | Approved | Date
1.0 | Initial version | Vy Dau | 2023-04-24
[Please delete this Template Change Log when making the Form]

## Guidelines (hidden)
<Agile - Scrum (MTX) Template> Guidelines
Purpose:
► Contains a series of deliverables(worksheets) that are created to document and track the execution and progression throughout all identified sprints. The content in this template is used to capturethe prioritized list of features to be implemented and provide a status of sprint and project execution..
Setting Up the Worksheet:
► Start with the provided worksheet template(s) ► Add, remove, or rename column headers as needed to support the needs of the project. ► Review the columns that contain List Validation values. Determine if the values are appropriate for the project. Changes can be made by going to the Values tab and editing the existing values. Please note that the values will display in the drop-down list in the order that they are entered. If removing values or adding more values, edit the List Validation value range as appropriate so that blank values do not appear in the drop-down list.
Usage:
► Documentation needed to capture the product backlog and the traceability of the development and implementation of user stories. The Project Manager should determine what content is needed and what values should be used for the deliverables contained herein.
► The Product Backlog is created at project initiation and updated and maintened throughout the project. The Product Backlog contains a prioritized list of features providing a short description of all functionality desired for the product. Each backlog item is estimated using user story points and then will be assigned to a sprint based upon velocity.
► The Project Release Plan is created using the identfied velocity and story points for each sprint and assigning target start and complete dates. The Project Release Plan generates the Product Burndown Chart to show progress towards completion of the project. The actual points and actual burn is updated throughout the project to generate a current Product Burndown Chart.
► The Project Volatility Chart captures all factors that might adversly effect the targeted time frames for completing a sprint. Volatility is the factor that determines confidence in a given estimates. An item is considered highly volatile if there are external factors that influence the eventual outcome. For each factor identified, the impact is assigned story points to be included when estimating the sprint. For each of the factors that can influence the project the entry should be placed in the Volatility Chart. When estimating volatility, it should be consitant with the estimation of story points used to estimate stories in Scrum i.e. using relative criteria.
► The Sprint Backlog & Burndown is a list of tasks to be completed during the sprint. The Sprint Burndown tracks the progress of each task associated with each story for the sprint.
Content:
Product Backlog ► ID: Tracking number used to identify a listed feature. ► Story/Feature/Request: A short description identifying what feature work, bug, technical work, or knowledge acquisition needs to be executed for the product. ► Category: A grouping of identified backlog items to help in prioritizing and assigning backlog items to a sprint. ► Type: This is a grouping to identify whether the backlog item is a new feature or a bug. In addition, other types of activities to prepare for a sprint can also be captured such as technical work or knowledge acquisition needed to prepare for a sprint. ► Sprint: The sprint number for which the backlog item is assigned. ► Priority: The priority assginged to a story/feature/request. ► Story/Epic: Indicate if the item is an Epic or an item that can be built and delivered in a single iteration ► Story Points: Once the story points have been estimated, they should be included in this column to assist in assigning backlog items to a sprint. Use the Fibonacci sequence to assign story points ► Estimated Hours: Estimate of the number of hours needed to complete the identified backlog item.
Project Report At the top left of this worksheet, the following should be captured: ► Project Name: Name of the project or release within the project that is associated with the identified sprints. ► Planned Velocity: The calculated velocity, the agile metric used to track, forecast, and communicate progress, needs to be included here for each applicable sprint. ► Current Velocity: The current velocity should be updated at predetermined intervals to be able to see accurately the current burndown of the project.. ► Planned Sprints: The total number of planned sprints for the project. ► Project Start Date: The date in which work commenced for the project. At the bottom of this worksheet, the following should be captured: ► Sprint: Sprint number assigned to the designated sprint. ► Start: The actual start date that worked commenced on the identified sprint. ► End: The actual completion date of the identified sprint. ► Planned Points: The total number of planned points associated to the sprint. ► Actual Points: The actual points captured at the end of a sprint. ► Planned Burn: The targeted burn for each sprint. ► Actual Burn: The actual burn captured during the execution of the sprint.

## Product Backlog
Product Backlog
[ On this worksheet, fictious data has been entered to show utilization of this tempate until a project example for this template is created.
` | Open | 0
| On-going | 0
| Done | 0
| Available | 0
| Removed | 0
| Total | 0
ID | Story / Feature / Request | Type | Status | Sprint | Priority | Team
| Common | Feature
1 | [FSCMS] Design/execute script to create database | Story | New | 1 | Medium
2 | [FSCMS] Create project structure | Story | New | 1 | Medium
3 | [FSCMS] Define coding rule | Story | New | 1 | Medium
4 | [FSCMS] Create common function/method | Story | New | 1 | Medium
| Member management | Feature
5 | [FSCMS] Add new members to the system | Story | New | 1 | Medium
6 | [FSCMS] Update member information | Story | New | 1 | Medium
7 | [FSCMS] Delete members from the system | Story | New | 1 | Medium
8 | [FSCMS] Import member information from file | Story | New | 1 | Medium
9 | [FSCMS] View and search list of members | Story | New | 1 | Medium
10 | [FSCMS] Export list of members | Story | New | 1 | Medium
| Dashboard management | Feature
11 | [FSCMS] Visualize data UT of members | Story | New | 1 | Medium
12 | [FSCMS] Visualize data skills of members | Story | New | 1 | Medium
13 | [FSCMS] Visualize data levels of CoE | Story | New | 1 | Medium
14 | [FSCMS] Export dashboard to report | Story | New | 1 | Medium
| Group management | Feature
15 | [FSCMS] Add new group | Story | New | 1 | Medium
16 | [FSCMS] Update group information | Story | New | 1 | Medium
17 | [FSCMS] Delete a group from system | Story | New | 1 | Medium
18 | [FSCMS] Add members to group | Story | New | 1 | Medium
19 | [FSCMS] Remove members from group | Story | New | 1 | Medium
Total | 19
Sprint Goals:
1. Sprint plainning is reviewed.
2. Screen Mockups are reviewed.
3. Demo Web Layout
4. Demo Grafana
Note on A11: ID: Tracking number used to identify a listed feature
Note on B11: Story/Feature/Request: A short description identifying what feature work, bug, technical work, or knowledge acquisition needs to be executed for the product.
Note on C11: Type: This is a grouping to identify whether the backlog item is a new feature or a bug. In addition, other types of activities to prepare for a sprint can also be captured such as technical work or knowledge acquisition needed to prepare for a sprint.
Note on E11: Sprint: The sprint number for which the backlog item is assigned.
Note on F11: UST420s: The priority assginged to a story/feature/request.
Note on G11: Story/Epic: Indicate if the item is an Epic or an item that can be built and delivered in a single iteration

## User story detail
No. | US title | US Detail
1 | [FSCMS] Add new members to the system | As a user, I want to be able to add a new member to the system so that I can keep track of all members. Function detail: - Some information must be validated before instert to DB. Each error must be have message ID and message error - Each member will belong to a group. If not select group, assign to "General" group as default. - User can choose group on pulldown and can quick add a group if not exitst
2 | [FSCMS] Update member information | As a user, I want to be able to update an existing member's information so that I can keep their information up-to-date. Function detail: - All information of member get via member Id and display to corresponding item on screen - Some information must be validated before update to DB. Each error must be have message ID and message error - Each member will belong to a group. If not select group, assign to "General" group as default. - User can choose group on pulldown and can quick add a group if not exitst
3 | [FSCMS] Delete members from the system | As a user, I want to be able to delete a member from the system so that I can remove their information if necessary. Function detail: - If use select action delete, show a popup/dialog to confirm - Don't make physical delete, only logical delete (change flg on DB)
4 | [FSCMS] Import member information from file | As a user, I want to be able to import member information from a file with a template so that I can easily add multiple members at once. Function detail: - User can select file to import, format maybe a csv file or excel file - If file not correct format, display error to user - Validate all lines before handle insert to DB - Display review screen before insert (Don't need implement on Sprint 1) - During the processing, if any record occurs the error => skip and process to next record. All error records must be show to import result screen, notify to user list of line have error on file. - Display import result to screen + If have validate error: Display message with format for each line: [Line index]-[Item name]: [Message] + Display number of record has been successfully, number of record has error (if any) and attach list of line index
5 | [FSCMS] View and search list of members | As a user, I want to be able to view and search information of members data in the system so that I can see an overview of all members and can filter base on my criteria Function detail: - Show all member as default - Support sort and paging - If user select more than one condition to search => Result must be return by combine all condition
6 | [FSCMS] Export list of members | As a user, I want to be able to export the list of members, so that we can create reports or share the member list with others. Function detail: - User can export current page or all page - Support format: CSV, Excel
7 | [FSCMS] Visualize data UT of members | As a user, I want to be able to view data UT (Utilization) of members visualized by chart so that I can know resource utilization of CoE. Function detail: - Visualized by Pie chart - User can quick view list of members for each type in chart (ex: view list members has UT > 80%) - Can filter by week, month, quarter and year
8 | [FSCMS] Visualize data skills of members | As a user, I want to be able to view data skills of members visualized by chart so that I can overview skills of member in CoE Function detail: - Visualized by Pie chart - Show 6 parts corresponding to 6 skills at most and 1 part "other". (Can change 6 to other depending on the situation at develop) - User can quick view list of members for each type in chart (ex: view list members has skill Reactjs) - Can filter by week, month, quarter and year
9 | [FSCMS] Visualize data levels of CoE | As a user, I want to be able to view data levels of members visualized by chart so that I can know number of members for each level. Function detail: - Visualized by Bar chart - User can quick view list of members for each type in chart (ex: view list members with level C2) - Can filter by week, month, quarter and year
10 | [FSCMS] Export dashboard to report | As a user, I want to be able to export dashboard to file so that I can create report or share to others. Function detail: - User can export specific or all chart - User can export list of members corresponding to each chart - Support format: Excel, CSV, PDF
11 | [FSCMS] Add new group | As a user, I want to be able to add new group so that I can add member to these group. Function detail: - Validate group name before insert to Database - User can quick add group on screen "Add/update Member"
12 | [FSCMS] Update group information | As a user, I want to be able to add update information of group so that I can change some information for group. Function detail: - Validate group name before insert to Database
13 | [FSCMS] Delete a group from system | As a user, I want to be able to delete a group from the system so that I can remove group if necessary. Function detail: - If use select action delete, show a popup/dialog to confirm - Don't make physical delete, only logical delete (change flg on DB)
14 | [FSCMS] Add members to group | As a user, I want to be able to add members to group so that I can assign members to different groups for easy management Function detail: - User can add member at screen: + Add new group + Update group + Add new member + Update member
15 | [FSCMS] Remove members from group | As a user, I want to be able to remove members from group so that I can remove member out of group if necessary. Function detail: - If use select action delete, show a popup/dialog to confirm

## Project Release Plan (hidden)
Project Release Plan
[ On this worksheet, fictious data has been entered to show utilization of this chart and generation of the chart until a project example for this template is created.
Project Name |  |  | Full-stack CoE Management System
Planned Velocity |  |  | #REF!
Current Velocity |  |  | 0
Planned Sprints |  |  | 0
Project Start Date |  |  | 2022-01-24
Instructions: |  |  | [In this section, identify any specific guidelines for when and how to update the Project Release Plan data and generation of the Project Burndown Chart.]
Release | Sprint2 | Start | End | Planned Points | Actual Points | Planned Burn | Actual Burn
[6 empty] | #REF! | 37
Release 1 | 0 | 2022-01-24 | #REF! | #REF! | 0 | #REF! | 37
|  |  |  | #REF! | 0
Velocity for this team 37 points/sprint.
Actual Velocity Team |  | 0 | Point/Sprint
Note on B5: Planned Velocity: The calculated velocity, the agile metric used to track, forecast, and communicate progress, needs to be included here for each applicable sprint.
Note on B6: Current Velocity: The current velocity should be updated at predetermined intervals to be able to see accurately the current burndown of the project.
Note on B7: Planned Sprints: The total number of planned sprints for the project.
Note on B21: Sprint: Sprint number assigned to the designated sprint.
Note on D21: Start: The actual start date that worked commenced on the identified sprint.
Note on E21: End: The actual completion date of the identified sprint.
Note on F21: Planned Points: The total number of planned points associated to the sprint.
Note on G21: Actual Points: The actual points captured at the end of a sprint.
Note on H21: Planned Burn: The targeted burn for each sprint.
Note on I21: Actual Burn: The actual burn captured during the execution of the sprint.

## Sprint 1
No. | Task ID | Work Item type | Title | State | Estimate (h) | PIC | Comments
1 |  | STORY |  | NEW
2 |  | STORY |  | NEW
3 |  | STORY |  | NEW
4 |  | STORY |  | NEW
5 |  | STORY |  | NEW
6 |  | STORY |  | NEW
0

## US01
User Story
[FSCMS] Add new members to the system
Task | Detail | DEV | UNIT TEST | TESTING
Some information must be validated before instert to DB. Each error must be have message ID and message error | Check if the email is valid and not already exists. | 2 hours | 2 hours
| Check if the Idap is existed or null. | 2 hours | 2 hours
| Check if the hcc_id is existed or null | 2 hours | 2 hours
| Check if the hire date is not empty or null and is a valid date format (legalEntityHireDate) | 2 hours | 2 hours
| Check if the business unit ID is not exists (FK) | 2 hours | 2 hours
| Select employeeEvaluations1 (allow null) | 2 hours | 2 hours
| Select employeeEvaluations2 (allow null) | 2 hours | 2 hours
| Select EmployeeSkill (allow null) | 2 hours | 2 hours
| Select ProjectFeedback (allow null) | 2 hours | 2 hours
| Check if the name is not empty or null | 2 hours | 2 hours
| Check if the location ID is not empty or null and exists | 2 hours | 2 hours
| Create Api | 2 hours | 2 hours
Assign member to a group | If the business unit ID is not provided, assign the member to the "General" group by default.
Get list of available BU for the user to choose
Allow user to select group from a dropdown |  | 2 hours | 2 hours
Create BU | Validate that the code is not empty or null and does not already exist in the system. | 2 hours | 2 hours
Add the new group to the business unit if it passes validation.

## US05
User Story
[FSCMS] search list of members Story New 1 Medium -- (API) Nien
Task | Detail | DEV | UNIT TEST | TESTING | Research
Show all member as default | Show all user if don't have condition (default) | 2 hours | 2 hours
| Search theo Ldap | 2 hours | 2 hours
| Search theo Hcc_id | 2 hours | 2 hours
| Search theo name | 2 hours | 2 hours |  |  | As a user, I want to be able to view and search information of members data in the system so that I can see an overview of all members and can filter base on my criteria Function detail: - Show all member as default - If user select more than one condition to search => Result must be return by combine all condition
| Search theo email | 2 hours | 2 hours
| Search theo practice | 2 hours | 2 hours
| Search theo coe_core_team_id | 2 hours | 2 hours
If user select more than one condition to search => Result must be return by combine all condition | Search on Params when user fill input | 2 hours | 2 hours
Create Api
|  |  | name | descreption
|  |  | phu | data

## RETROSPECTIVE
SPRINT RETROSPECTIVE
SPRINT ID | START - Useful things | STOP - Not Good things | KEEP - Good things | MORE - Things to continue/enhance | LESS - Things should reduce
1 | Add User demo to product review process. | Extending the Daily Scrum meeting, max duration should be 15 mins. | Circulating Daily Scrum meeting notes on email. | Communications to the Project Board. | Nothing at present.
Note on C5: stakeholdermap.com: What the team will start doing.
Note on D5: stakeholdermap.com: What the team will stop doing.
Note on E5: stakeholdermap.com: Actions the team will keep doing.
Note on F5: stakeholdermap.com: Actions that need to be done more often.
Note on G5: stakeholdermap.com: Actions that the team will do less of in the next sprint.